## Instruction
Maintenance Management System (MMS) Template for Capital Maintenance Agreement (CMA) Compliance
1. Prior to the use, update all sections in Blue text in each tab including dropdown lists in "List" tab.
CMA MMS Requirements (V5.0)
CMA Specification Item 9 - Section 9.6:
DB Contractor shall implement a system (the “Maintenance Management System” or “MMS”) to store all the following Maintenance Records:
- description, picture (showing GPS coordinates, location, date-time) of identification and categorization of Defects;
- planned actions including traffic control plan and repair procedure, and date-time for scheduled and actual permanent repair of all Defects, [and] date of contractual cure period[, and running total of non-compliance points];
- details including date-time of actual repairs performed with inspection tests/reports and associated pictures of repairs (showing GPS coordinates, location and date-time);
- complaints and reports received from TxDOT and third parties; and
- accidents and incidents relating to the Maintenance Services.
Maintenance Records shall be organized by Performance Section. All Defects shall be recorded in the MMS promptly after coming to the attention of DB Contractor.
All other recording requirements shall be recorded on the MMS within 15 days of completion or occurrence of the relevant activity.
When a Maintained Element is constructed, installed, maintained, inspected, modified, replaced or removed, DB Contractor shall create and store a Maintenance Record no later than three days after completion of such work.
DB Contractor shall provide TxDOT real-time, remote access to the Maintenance Records for the duration of the Maintenance Period.
Attachment 9-1 Note 1:
DB Contractor shall record a separate Defect upon failure to achieve any of the requirements set forth in a Measurement Record.

## Defect
Defect Log
Project Name: | example |  | Last Update: | 1/1/2022
District: | example
Organization: | example
Work Status | Number of Defects |  | Compliance Status | Number of Defects
Completed | 2 |  | Not Repaird - Overdue | 1
Ongoing | 2 |  | Repair completed but after Due Date | 7
Not started | 7
On hold | 5
TxDOT Step-in | 4
Total | 20 |  | Note: Rows hidden will not be counted.
A. Defect Identification | [10 empty] | B. Defect Repair | [9 empty] | C. Verification |  |  | D. Miscellaenous
Defect # | Date of Identification | Time of Identification | Categorization | Element Category | Location (Performance Section) | Location (TRM) | Location Description | Source of Identification | Cause of Defect | Defect Description | Work Order # | Date of Repair | Time of Repair | Repair Type | TxDOT Function Codes | Work Status | Defect Repair Period (days) | Contractual Due Date | Compliance Status? | Repair Description | Date of Verificaiton | Person Name of Verificaiton | Verification Description | Photos | NBI Number (bridge only)
D-1 | 2021-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | General Inspection | Third Party Damage |  |  |  | 0:00 | Temporary Repair |  | Not started | 180 | 2021-09-10 | Not repaird - Overdue |  |  |  |  | #1, #4
D-2 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | DB Contractor | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Ongoing | 180 | 2022-09-10 | [5 empty] | #1, #4
D-3 | 2021-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | DB Contractor | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Ongoing | 180 | 2021-09-10 | Repair completed but after Due Date |  |  |  |  | #1, #4
D-4 | 2021-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | DB Contractor | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | On hold | 180 | 2021-09-10 | Repair completed but after Due Date |  |  |  |  | #1, #4
D-5 | 2019-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | DB Contractor | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | On hold | 180 | 2019-09-10 | Repair completed but after Due Date |  |  |  |  | #1, #4
D-6 | 2019-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | DB Contractor | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | On hold | 180 | 2019-09-10 | Repair completed but after Due Date |  |  |  |  | #1, #4
D-7 | 2019-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | On hold | 180 | 2019-09-10 | Repair completed but after Due Date |  |  |  |  | #1, #4
D-8 | 2019-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | On hold | 180 | 2019-09-10 | Repair completed but after Due Date |  |  |  |  | #1, #4
D-9 | 2019-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | TxDOT Step-in | 180 | 2019-09-10 | Repair completed but after Due Date |  |  |  |  | #1, #4
D-10 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | TxDOT Step-in | 180 | 2022-09-10 | [5 empty] | #1, #4
D-11 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | TxDOT Step-in | 180 | 2022-09-10 | [5 empty] | #1, #4
D-12 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | TxDOT Step-in | 180 | 2022-09-10 | [5 empty] | #1, #4
D-13 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Completed | 180 | 2022-09-10 | [5 empty] | #1, #4
D-14 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | TxDOT | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Completed | 180 | 2022-09-10 | [5 empty] | #1, #4
D-15 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | Third Party | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Not started | 180 | 2022-09-10 | [5 empty] | #1, #4
D-16 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | Third Party | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Not started | 180 | 2022-09-10 | [5 empty] | #1, #4
D-17 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | Third Party | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Not started | 180 | 2022-09-10 | [5 empty] | #1, #4
D-18 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | Third Party | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Not started | 180 | 2022-09-10 | [5 empty] | #1, #4
D-19 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | Third Party | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Not started | 180 | 2022-09-10 | [5 empty] | #1, #4
D-20 | 2022-03-14 | 0:00 | Category 1 | Pavement | GPL_NB_001 |  |  | Third Party | Third Party Damage |  |  | 2022-04-14 | 0:00 | Temporary Repair |  | Not started | 180 | 2022-09-10 | [5 empty] | #1, #4
Formulas:
Contractual Due Date = IF([example]=0,"",[example]+[Defect Repair Period (days)])

## Accident
Accident or Incident Log
Project Name: | example |  | Last Update: | 1/1/2022
District: | example
Organization: | example
# of Injuries or Fatalities
Injuries | 21
Fatalities | 40
Note: Rows hidden will not be counted.
Accident
Accident or Incident # | Associated Defect # (if applicable) | Date of Accident | Time of Accident | Location (Performance Section) | Location (TRM) | Location Description | Accident Type | Injuries Reported | Fatalities Reported | HazMat | Accident or Incident Description
A-1 | D-1 | 2021-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 2 | 2 | Yes
A-2 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Injury during work | 1 | 2
A-3 |  | 2021-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-4 |  | 2021-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-5 |  | 2019-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-6 |  | 2019-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-7 |  | 2019-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-8 |  | 2019-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-9 |  | 2019-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-10 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-11 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-12 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-13 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-14 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-15 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-16 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-17 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-18 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-19 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2
A-20 |  | 2022-03-14 | 0:00 | GPL_NB_001 |  |  | Vehicle Incident | 1 | 2

## Complaint
Complaint Log
Project Name: | example |  | Last Update: | 1/1/2022
District: | example
Organization: | example
Complaint Status | Number of Complaint
Open | 19
Closed | 1
Total | 20
Note: Rows hidden will not be counted.
Compliant
Complaint # | Received Date | Status | Name | Contact Information | Type | Description | Initial Response Date | Response Note | Resolution Date
C-1 | 2021-03-14 | Open |  |  | Complaint |  | 2021-03-14 |  | 2021-03-14
C-2 | 2022-03-14 | Closed |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-3 | 2021-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-4 | 2021-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-5 | 2019-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-6 | 2019-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-7 | 2019-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-8 | 2019-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-9 | 2019-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-10 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-11 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-12 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-13 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-14 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-15 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-16 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-17 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-18 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-19 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14
C-20 | 2022-03-14 | Open |  |  |  |  | 2021-03-14 |  | 2021-03-14

## List
Tab Name | Defect | Defect | Defect | Defect | Defect | Defect | Defect | Defect | Accident | Accident | Complaint | Complaint | Complaint
Pulldown List | Performance Section (vary by project) | Maintained Element Category | Repair Type | Defect Repair Period | Defect Categorization | Source of Defect Identification | Cause of Defects | Status | Accident Type | HazMat | Source of Complaint | Type | Status
| GPL_NB_001 | Pavement | Temporary Repair | 1 | Category 1 | DB Contractor | General Wear and Tear | Completed | Vehicle accident | Yes | TxDOT | Inquiry | Closed
| GPL_NB_002 | Structures | Hazard Mitigation | 90 | Category 2 | TxDOT | Third Party Damage | Ongoing | Injury during work | No | Third Party | Complaint | Open
| GPL_NB_003 | Drainage | Permanent Repair | 180 |  | Third Party | Accidents and Incidents by DB Contractor | Not started | Emergency event |  | …
| GPL_NB_004 | Earthwork |  |  |  | General Inspection | Nonconforming Work | On hold | …
| GPL_NB_005 | … |  |  |  | … | Unknown | TxDOT Step-in
| GPL_SB_001 | [5 empty] | ….
GPL_SB_002
GPL_SB_003
GPL_SB_004
GPL_SB_005
FR_NB_001
FR_NB_002
FR_NB_003
FR_NB_004
FR_NB_005
FR_SB_001
FR_SB_002
FR_SB_003
FR_SB_004
FR_SB_005
…